## part I D
PART I- D |  | Timely Project Completion Status [may use separate sheet]
Project Title | Residential Complex Development (Project name and its Activities and Taks indicated above are illustrative. The tasks and activiteies and related details are to be as per schedule submitted in DPRs for the project)
Phase | Activities | Tasks(e.g only) | Taskwise Cost (in Cr.) | Taskwise Cost Incurred (in Cr.) | Part of Loan Installment no. (I, II, III or IV) | Date of Completion |  | Assessment for Eligibility on Timely Completion | If slag | Third Party Inspection | Third Party Report | Incentive Eligibility status for timely completn.
[6 empty] | Due Date | Actual Date of Completion
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Land Acquisition | section 4 notification |  | 0.25 |  | I
| sec 6 notification |  | 0.25 |  | I
| Compensation disbursement |  | 5.5 |  | II
Sewer network | Sewerline laying |  |  |  | I
Srwage Treatment
Road Network development
| road | basework |  |  | I
|  | earthfilling /cutting |  |  | I
|  | Bitumin Laying |  |  | III
|  | Street Furniture |  |  | IV
bridge
ROB
Housing development | Buliding structures | Foundation laying |  |  | II
|  | Pliiars and Columns |  |  | II
|  | Walls |  |  | II
|  | Outer Wall finishing |  |  | III
| Electric Supply | Install transformers |  |  | II
|  | InstallElectricity poles |  |  | III
Watersuplly
TOTAL
Note: i) Item 9,-13 to be filled up as per Coding table given below
…….ii) In item 5 and 8 Quantity/ Percentage of work completed and expenditure incurred upto the reporting month should be given in Monthly reports till actual completion of the task.
Codes to be used while filling up the above proforma
Item S.No. |  | Options & Respective Codes |  |  | Item S.No. | Options & Respective Codes
9 |  | Slag [1]; No Slag [2] |  |  | 11 | Due [1]; Done [2]
10 |  | No Slag [0]; If slag then duration in weeks [ 1,2 …n] |  |  | 12 | Due [1]; Recieved [2]
[5 empty] | 13 | Yes [1]; No [2]

## part I B
PART I-B
Post Sanction Modalities
Loan Details
Date of Sanction of Ist Loan Installment |  |  |  | Date of Disbursement of 1st Loan Installment
Date of Withdrawal of Project [if applicable]
Timely Installment Withdrawal Status
Sr. No. of Loan Installment | Date of Actual Withdrawal from NCRPB | Date of Actual Disbursement of State / Agency's Share | Utilisation Certificate Submitted | Third Party Inspection | Third Party Inspection Report | Assessment for eligibility for Timely Withdrawal of loan Incentive
|  |  | 1 | 2 | 3 | 4
Ist
2nd
3rd.
4rth
Total Amount Withdrawn [in Cr.]
Note:1,2,3 & 4 to be filled up codes as per Coding table given below
Codes to be used while filling up the above proforma
Item S.No. | Options & Respective Codes
1 | Yes [1]; No [2]
2 | Due [1]; Done [2]
3 | Due [1]; Recieved [2]
4 | Yes [1]; No [2]

## Part A item 21
PART I - A Contd…
21 | Repayment Schedule
| Sr. No. of Loan Installment | Year | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
| I | Installment of Principal + Interest Amount to be paid [in Cr.]
Due date for payment [ day/month / year]
| II | Installment of Principal + Interest Amount to be paid [in Cr.]
Due date for payment [ day/month / year]
| III | Installment of Principal + Interest Amount to be paid [in Cr.]
Due date for payment [ day/month / year]
| IV | Installment of Principal + Interest Amount to be paid [in Cr.]
Due date for payment [ day/month / year]

## Part I- C
PART I - C
Timely Repayment Schedule for Installments [Principal & Interest]
Sr. No. of Loan Installment | Year | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
I | Installment of Principal + Interest Amount to be paid [in Cr.]
Actual Amount paid [in Cr.]
Actual date for payment [ day/month / year]
Balance Amount due if any [in Cr.]
Status [default/delay]*
Delayed by (no. of days)
Penalty Amount [in Cr.]
Incentive Eligibility **
II | Installment of Principal + Interest Amount to be paid [in Cr.]
Actual Amount paid [in Cr.]
Actual date for payment [ day/month / year]
Balance Amount due if any [in Cr.]
Status [default/delay]*
Delayed by (no. of days)
Penalty Amount [in Cr.]
Incentive Eligibility **
III | Installment of Principal + Interest Amount to be paid [in Cr.]
Actual Amount paid [in Cr.]
Actual date for payment [ day/month / year]
Balance Amount due if any [in Cr.]
Status [default/delay]*
Delayed by (no. of days)
Penalty Amount [in Cr.]
Incentive Eligibility **
IV | Installment of Principal + Interest Amount to be paid [in Cr.]
Actual Amount paid [in Cr.]
Actual date for payment [ day/month / year]
Balance Amount due if any [in Cr.]
Status [default/delay]*
Delayed by (no. of days)
Penalty Amount [in Cr.]
Incentive Eligibility **
Note: | * Code to be used Not applicable [0]; Default [1]; Delay [2]
** Code to be used : Yes [1]; No [2]

## part I A cont 2
PART I - A Contd…
20 | Loan Disbursement Schedule
| Sr. No. of Loan Installment | Amount to be Released by NCRPB [in Cr.] | Due Date for release(date/ quarter) | Amount to be Released as State / Agency's Share [in Cr.] | Due Date for release(date/ quarter) | Total Estimated Cost [in Cr.]
Ist
2nd
3rd.
4rth
Grand Total
20 A | Conformity to Plans
| Plan | Conformity status | Incentive Applicable | Codes to be used while filling up the proforma
|  | 1 | 2 |  | Item S.No. | Options & Respective Codes
| Regional Plan |  |  |  | 1 | Yes [1]; No [2]
| Functional Plan |  |  |  | 2 | 0.1% [1]; 0% [2]
District Plan
Sub Regional Plan
Master Plan
Total Plan Conformation Incentives Applicable

## part 1-a CONT 1
PART I - A Contd…
19 | PERT Chart
| Project Title | Phase | Activities | Tasks(e.g only) | Taskwise Cost (in Cr.) | Part of Loan Installment no. (I, II, III or IV) | Date of Completion
| Residential Complex Development |  | section 4 notification |  | 0.25 | I
|  |  | sec 6 notification |  | 0.25 | I
|  |  | Compensation disbursement |  | 5.5 | II
|  | Sewer network | Sewerline laying |  |  | I
Srwage Treatment
Road Network development
|  |  | road | basework |  | I
|  |  |  | earthfilling /cutting |  | I
|  |  |  | Bitumin Laying |  | III
|  |  |  | Street Furniture |  | IV
bridge
ROB
|  | Housing development | Buliding structures | Foundation laying |  | II
|  |  |  | Pliiars and Columns |  | II
|  |  |  | Walls |  | II
|  |  |  | Outer Wall finishing |  | III
|  |  | Electric Supply | Install transformers |  | II
|  |  |  | InstallElectricity poles |  | III
Watersuplly
Note: Activities and Taks indicated above are illustrative
The Activities are the main heads of works to be carried out and
the tasks are the sub activities to be carried out under each activity

## PART I A
PART I- A
Performa Related to General Project Monitoring Monthly Progress Report (Ongoing Projects)
1 | Project Name |  |  |  | 12 | Implementing Agency
2 | Project Type |  | [ please fillup codes as per Coding table given below] |  |  | Contact Person /Designation
3 | Project Status |  | [ please fillup codes as per Coding table given below] |  |  | Address/ phone / fax / email
4 | Reason for Withdrawl |  | [ please fillup codes as per Coding table given below]
5 | Project Location State |  |  |  | 13 | Loan Borrowing Agency
6 | District |  |  |  |  | Contact Person /Designation
7 | Town/City |  |  |  |  | Address/ phone / fax / email
8 | Project Area [Ha.] |  |  |  | 14 | Date of Loan Sanction
9 | Security Type [ please fillup codes as per Coding table given below] |  |  |  | 15 | Total Loan Sanction Amount [in Cr.]
10 | Project Sanctioning PSMG-I date & Meeting No. |  |  |  | 16 | Third Party Inspection Report Status [ pls. fillup codes as per Coding table below]
11 | Estimated Project Cost [in Cr.] |  |  |  | 17 | Date of Physical Completion
[5 empty] | 17A | Revised Date of Physical Completion
[5 empty] | 18 | Date of Financial Completion
Codes to be used while filling up the above proforma
|  | Item S.No. |  | Options & Respective Codes
|  | 2 | Water (1); Transport (2); Sewerage (3); Solid Waste Management (4); Land Development (5) ; Power (6); Any other (pls specify)
|  | 3 | Physically & Financially Ongoing [1]; Physically & Financially Completed [2]; Physically Completed & Financially Ongoing [3];
Physically Ongoing & Financially Completed [4]; Withdrawn[5]
|  | 4 | Submitted [1]; Not submitted [2]; Not Applicable[3]
|  | 9 | State Government Guarantee[1]; ESCROW Account[2]; Collateral Security (full)[3]; Collateral Paripasu Charge[4]; Guarantor [5]
|  | 16 | Satisfactory [1]; Unsatisfactory [2]
PART -I
Pre Sanction Modalities
1 | Detailed Project Report [DPR] Submitted |  |  |  | 5 | Date of DPR Submission [date/month/ year]
2 | Appraisal by National Institute [( due in 6 weeks) ] |  |  |  | 6 | Appraisal Report Received on [date/month/ year]
3 | Appointment of Third Party Inspection Agency/team |  |  |  | 7 | PSMG meeting to be taken up in*
4 | Third Party Inspection Agency/team [Name] |  |  |  | 8 | Decision of PSMG I meeting
Reply Codes (as applicable)
| Item No. | Options
| 1 | Yes [1]; No [2]
| 2 | Yes [1]; No [2]; Ongoing [3]
| 3 | Yes [1]; No [2]; Ongoing [3]
| 8 | Approved [1]; Not approved [2]; Approved with Conditions [3]; To be tken up in next PSMG meet [4]